# 10-Day Build Plan

Realistic execution plan for MVP

Project: PolicyBot Intelligence

Updated: 2026-06-18

# 1. Goal

Build a strong MVP of PolicyBot Intelligence in 10 days with real RAG, vector DB, metadata, freshness checks, trace UI, scoring, Docker setup, and basic evaluation.

# Day 1: Project setup and architecture skeleton

Deliverables:

Git repo structure.

FastAPI app skeleton.

React + Tailwind app skeleton.

Docker Compose with MongoDB, Redis, Qdrant.

`.env.example`.

Health endpoints.

Acceptance:

`docker compose up` starts services.

Backend docs open at `/docs`.

Frontend opens locally.

# Day 2: MongoDB schemas and vector DB adapter

Deliverables:

MongoDB connection.

Repository layer.

Collections/index creation command.

`VectorStoreAdapter` interface.

Qdrant implementation.

Pinecone placeholder implementation.

Acceptance:

Can create Qdrant collection.

Can upsert/search dummy vectors.

MongoDB indexes are created.

# Day 3: Document ingestion pipeline

Deliverables:

Folder scanner.

File hash detection.

Basic loaders for PDF, DOCX, TXT, MD.

Metadata extraction.

Chunking.

Acceptance:

Can scan folder and create document/chunk records.

Unchanged files are skipped.

# Day 4: Embeddings and vector indexing

Deliverables:

Gemini embedding provider.

Batch embedding.

Vector DB upsert.

Reindex document command.

Delete vectors by document ID.

Acceptance:

Real document chunks are searchable by semantic query.

# Day 5: LangGraph RAG workflow

Deliverables:

Graph state.

Query rewrite node.

Embed query node.

Retrieve candidates node.

Rerank node.

Context builder node.

Gemini answer generation node.

Acceptance:

`/chat/ask` returns answer with sources.

# Day 6: Freshness resolver and conflict detection

Deliverables:

Effective date extraction.

Version extraction.

Freshness ranking.

Conflict detection.

Source freshness labels.

Acceptance:

If old and new documents match, latest is preferred.

Conflicts appear in response warnings.

# Day 7: Trace timeline and frontend chat

Deliverables:

Trace event writer.

SSE trace stream.

Chat page.

Trace timeline component.

Source cards.

Acceptance:

User can ask a question and watch steps.

# Day 8: Scoring and evaluation dashboard

Deliverables:

Retrieval score.

Citation coverage score.

Freshness confidence score.

Conflict risk score.

Evaluation dataset format.

Evaluation page.

Acceptance:

Each answer shows scores.

Evaluation run can test sample questions.

# Day 9: Document admin UI and Docker polish

Deliverables:

Documents page.

Ingestion page.

Job status UI.

Docker improvements.

Makefile commands.

Setup docs.

Acceptance:

Admin can sync folder and see indexed files.

# Day 10: QA, demo data, deployment prep

Deliverables:

Test documents.

Demo script.

QA checklist.

Deployment guide.

Final README.

Bug fixes.

Acceptance:

Full demo works end-to-end.

Client can understand product value.

# 2. MVP risk control

Do not overbuild these in first 10 days:

complex auth,

cloud file connectors,

fancy admin dashboards,

multiple vector DB providers fully implemented,

deep analytics.

Build clean interfaces first, implement Qdrant fully, then Pinecone next.

# 3. Best delivery strategy

Use this order:

Working RAG core → source quality → trace UI → scoring → admin polish

Do not start with only UI. The core value is retrieval quality.