## Dashboard
PolicyBot Intelligence — Build Tracker Dashboard
Metric | Value |  | Status | Count | Current Focus | Instruction
Total Tasks | 65 |  | Done | 0 | Default vector DB | Qdrant local Docker
Done | 0 |  | In Progress | 0 | Metadata DB | MongoDB
In Progress | 0 |  | Blocked | 0 | Default LLM | Gemini provider
Blocked | 0 |  | In Review | 0 | Default UI | React + Tailwind
In Review | 0 |  | Not Started | 65 | Tracking rule | Update tracker after every phase
Not Started | 65 |  |  |  | MVP flow | Local ingest → Query → Trace UI
Completion % | 0%
Area | Total | Done | Blocked | Completion %
Backend | 17 | 0 | 0 | 0%
Frontend | 12 | 0 | 0 | 0%
Infra | 4 | 0 | 0 | 0%
RAG | 6 | 0 | 0 | 0%
Vector DB | 4 | 0 | 0 | 0%
MongoDB | 4 | 0 | 0 | 0%
Google Drive | 1 | 0 | 0 | 0%
Docs | 8 | 0 | 0 | 0%
Testing | 4 | 0 | 0 | 0%
Evaluation | 2 | 0 | 0 | 0%
Security | 1 | 0 | 0 | 0%
Observability | 2 | 0 | 0 | 0%

## Task Tracker
ID | Phase | Area | Task | Acceptance Criteria | Priority | Status | Owner | Estimate Days | Target Day | Dependencies | Notes | Last Updated
PB-001 | Phase 1 Foundation | Infra | Create repository structure | Create backend, frontend, docs, scripts, templates folders exactly as required. | P0 | Not Started | Dev | 0.5 | Day 1
PB-002 | Phase 1 Foundation | Backend | Create FastAPI app skeleton | App starts, exposes /api/v1/health, includes router layout and CORS. | P0 | Not Started | Dev | 0.5 | Day 1 | PB-001
PB-003 | Phase 1 Foundation | Frontend | Create React Vite TypeScript app | App boots locally, Tailwind configured, routes initialized. | P0 | Not Started | Dev | 0.5 | Day 1 | PB-001
PB-004 | Phase 1 Foundation | Infra | Add Docker Compose baseline | MongoDB, Qdrant, backend, and frontend services defined. | P0 | Not Started | Dev | 0.5 | Day 1 | PB-002, PB-003
PB-005 | Phase 1 Foundation | Infra | Add Makefile commands | make setup/dev/docker-up/docker-down/test/logs commands documented and working. | P0 | Not Started | Dev | 0.3 | Day 1 | PB-004
PB-006 | Phase 1 Foundation | Docs | Create first README | README explains project, stack, one-command startup, folder structure. | P1 | Not Started | Dev | 0.3 | Day 1 | PB-001
PB-007 | Phase 2 Config | Backend | Create Pydantic settings | All env vars loaded, typed, validated, and accessible via dependency. | P0 | Not Started | Dev | 0.5 | Day 1 | PB-002
PB-008 | Phase 2 Config | Backend | Create config API | GET/PATCH config endpoints support non-secret runtime settings. | P1 | Not Started | Dev | 0.4 | Day 2 | PB-007
PB-009 | Phase 2 Config | Frontend | Settings page skeleton | Settings page displays active LLM provider, vector DB, chunk size, top-k. | P1 | Not Started | Dev | 0.5 | Day 2 | PB-003, PB-008
PB-010 | Phase 3 MongoDB | MongoDB | Create async Mongo client | Motor client initialized, health check works, clean shutdown implemented. | P0 | Not Started | Dev | 0.5 | Day 2 | PB-007
PB-011 | Phase 3 MongoDB | MongoDB | Create repository base class | Reusable async CRUD helpers and collection access pattern. | P1 | Not Started | Dev | 0.4 | Day 2 | PB-010
PB-012 | Phase 3 MongoDB | MongoDB | Create core repositories | Sources, documents, chunks, jobs, traces, evaluation, config repos exist. | P0 | Not Started | Dev | 1 | Day 2 | PB-011
PB-013 | Phase 3 MongoDB | MongoDB | Create Mongo indexes | Indexes for source_id, document_id, hash, modified_at, job_id, trace_id. | P0 | Not Started | Dev | 0.4 | Day 2 | PB-012
PB-014 | Phase 4 Vector DB | Vector DB | Create BaseVectorStore interface | Abstract async methods for ensure_collection, upsert, search, delete. | P0 | Not Started | Dev | 0.4 | Day 3 | PB-007
PB-015 | Phase 4 Vector DB | Vector DB | Implement QdrantVectorStore | Qdrant collection auto-created, upsert/search/delete work. | P0 | Not Started | Dev | 1 | Day 3 | PB-014
PB-016 | Phase 4 Vector DB | Vector DB | Add vector store factory | Factory chooses qdrant/pinecone/chroma/mongo by env config. | P0 | Not Started | Dev | 0.5 | Day 3 | PB-014, PB-015
PB-017 | Phase 4 Vector DB | Vector DB | Add Pinecone/Chroma/Mongo skeleton adapters | Adapters compile and raise useful NotConfiguredError if missing settings. | P2 | Not Started | Dev | 0.6 | Day 3 | PB-016
PB-018 | Phase 5 LLM Providers | Backend | Create BaseLLMProvider and BaseEmbeddingProvider | Provider interfaces are async and model-agnostic. | P0 | Not Started | Dev | 0.4 | Day 3 | PB-007
PB-019 | Phase 5 LLM Providers | Backend | Implement Gemini provider | Gemini chat and embedding provider work using env config. | P0 | Not Started | Dev | 1 | Day 3 | PB-018
PB-020 | Phase 5 LLM Providers | Backend | Create provider factory | RAG services receive providers through factory/dependency injection. | P0 | Not Started | Dev | 0.5 | Day 3 | PB-019
PB-021 | Phase 5 LLM Providers | Backend | Add OpenAI/Anthropic/local skeletons | Skeleton adapters are clean and easy to complete later. | P2 | Not Started | Dev | 0.5 | Day 4 | PB-020
PB-022 | Phase 6 Ingestion | Backend | Create connector abstraction | BaseConnector supports list_files, get_metadata, download/read content. | P0 | Not Started | Dev | 0.5 | Day 4 | PB-012
PB-023 | Phase 6 Ingestion | Backend | Implement local folder connector | Scans .txt .md .pdf .docx .csv files and returns metadata. | P0 | Not Started | Dev | 1 | Day 4 | PB-022
PB-024 | Phase 6 Ingestion | Backend | Create document loaders | Text extraction works for MVP supported formats. | P0 | Not Started | Dev | 1 | Day 4 | PB-023
PB-025 | Phase 6 Ingestion | Backend | Create chunking strategy | Configurable chunk size/overlap with metadata preserved. | P0 | Not Started | Dev | 0.7 | Day 4 | PB-024
PB-026 | Phase 6 Ingestion | Backend | Create hash/version service | Unchanged files skipped, changed files versioned. | P0 | Not Started | Dev | 0.7 | Day 4 | PB-012, PB-024
PB-027 | Phase 6 Ingestion | Backend | Build ingestion service | End-to-end local folder indexing into MongoDB and Qdrant. | P0 | Not Started | Dev | 1 | Day 5 | PB-015, PB-019, PB-025, PB-026
PB-028 | Phase 6 Ingestion | Frontend | Build ingestion UI | Sources page can submit local folder path and show job progress. | P1 | Not Started | Dev | 0.8 | Day 5 | PB-027
PB-029 | Phase 7 Google Drive | Google Drive | Document Google OAuth setup | Docs explain client ID, API key, redirect URI, and scopes. | P0 | Not Started | Dev | 0.4 | Day 5 | PB-006
PB-030 | Phase 7 Google Drive | Frontend | Create Connect Google Drive button | Button starts auth/picker flow and shows connection state. | P0 | Not Started | Dev | 0.8 | Day 5 | PB-003, PB-029
PB-031 | Phase 7 Google Drive | Frontend | Implement Google Picker component | User can choose files/folder and see selected source cards. | P0 | Not Started | Dev | 1 | Day 6 | PB-030
PB-032 | Phase 7 Google Drive | Backend | Create Google Drive connector skeleton | Connector lists/downloads selected files; folder sync mode documented. | P0 | Not Started | Dev | 1 | Day 6 | PB-022, PB-031
PB-033 | Phase 7 Google Drive | Backend | Add Drive ingestion endpoints | picker-selection and folder-sync endpoints create source and ingestion job. | P0 | Not Started | Dev | 0.8 | Day 6 | PB-027, PB-032
PB-034 | Phase 8 RAG | RAG | Create query schemas | Query request/response includes answer, citations, scores, trace_id. | P0 | Not Started | Dev | 0.4 | Day 6 | PB-012
PB-035 | Phase 8 RAG | RAG | Create retrieval service | Vector search plus optional keyword search returns candidates. | P0 | Not Started | Dev | 0.8 | Day 6 | PB-015, PB-019
PB-036 | Phase 8 RAG | RAG | Create freshness resolver | Resolver prefers latest valid document using modified_at/version/hash. | P0 | Not Started | Dev | 0.8 | Day 6 | PB-035
PB-037 | Phase 8 RAG | RAG | Create reranker/context grader | Candidate chunks are sorted and filtered before prompt building. | P1 | Not Started | Dev | 0.8 | Day 7 | PB-035
PB-038 | Phase 8 RAG | RAG | Create prompt builder and citation service | Prompt includes context and citation rules; answer includes source references. | P0 | Not Started | Dev | 0.7 | Day 7 | PB-036, PB-037
PB-039 | Phase 8 RAG | RAG | Implement LangGraph RAG graph | All RAG nodes emit trace events and return final answer. | P0 | Not Started | Dev | 1.5 | Day 7 | PB-038, PB-020
PB-040 | Phase 8 RAG | Backend | Create query endpoint | POST /query runs graph and persists trace/session. | P0 | Not Started | Dev | 0.5 | Day 7 | PB-039
PB-041 | Phase 8 RAG | Frontend | Build chat page | User asks question, sees answer, citations, confidence, and trace link. | P0 | Not Started | Dev | 1 | Day 7 | PB-040
PB-042 | Phase 9 Observability | Observability | Create trace service | Trace events persisted with node name, timestamps, payload, score. | P0 | Not Started | Dev | 0.7 | Day 7 | PB-012
PB-043 | Phase 9 Observability | Backend | Create trace API | GET /traces/{trace_id} returns operational trace. | P0 | Not Started | Dev | 0.4 | Day 8 | PB-042
PB-044 | Phase 9 Observability | Frontend | Build trace timeline UI | Timeline shows query rewrite, retrieval, rerank, freshness, answer, scores. | P0 | Not Started | Dev | 1 | Day 8 | PB-043
PB-045 | Phase 9 Observability | Observability | Add structured logging | Backend logs include request_id, job_id, trace_id, latency, provider. | P1 | Not Started | Dev | 0.5 | Day 8 | PB-042
PB-046 | Phase 10 Evaluation | Evaluation | Create scoring service | Calculates retrieval, freshness, coverage, citation, confidence, latency scores. | P0 | Not Started | Dev | 1 | Day 8 | PB-039
PB-047 | Phase 10 Evaluation | Evaluation | Create evaluation backend | Golden dataset and eval run endpoints work. | P1 | Not Started | Dev | 1 | Day 8 | PB-046
PB-048 | Phase 10 Evaluation | Frontend | Build evaluation dashboard | Accuracy %, failed cases, and weak source table visible. | P1 | Not Started | Dev | 0.8 | Day 9 | PB-047
PB-049 | Phase 11 UI | Frontend | Create layout and sidebar | Responsive app shell with sidebar, header, active route, status badges. | P0 | Not Started | Dev | 0.8 | Day 5 | PB-003
PB-050 | Phase 11 UI | Frontend | Create dashboard page | Cards for docs, chunks, jobs, confidence, latency, provider, vector DB. | P1 | Not Started | Dev | 0.8 | Day 8 | PB-028, PB-041
PB-051 | Phase 11 UI | Frontend | Create multi-theme system | Black, white, blue, red, gradient, custom color and localStorage persistence. | P0 | Not Started | Dev | 1 | Day 8 | PB-049
PB-052 | Phase 11 UI | Frontend | Create settings page functionality | Model/vector/chunk/top-k settings UI connected to backend. | P1 | Not Started | Dev | 0.8 | Day 9 | PB-008, PB-051
PB-053 | Phase 12 Docs | Docs | Create product overview doc | Client-friendly product explanation and value proposition. | P1 | Not Started | Dev | 0.4 | Day 9 | PB-006
PB-054 | Phase 12 Docs | Docs | Create developer setup doc | Local setup, env, Docker, troubleshooting, commands. | P0 | Not Started | Dev | 0.6 | Day 9 | PB-005
PB-055 | Phase 12 Docs | Docs | Create architecture docs | Backend, frontend, full-stack, data flow, RAG flow documented. | P0 | Not Started | Dev | 0.8 | Day 9 | PB-039
PB-056 | Phase 12 Docs | Docs | Create API reference docs | Every endpoint documented with request/response examples. | P1 | Not Started | Dev | 0.6 | Day 9 | PB-040, PB-043, PB-047
PB-057 | Phase 12 Docs | Docs | Create implementation tracker files | CSV and MD trackers exist and are updated by phase. | P0 | Not Started | Dev | 0.3 | Day 1 | PB-001
PB-058 | Phase 13 Testing | Testing | Backend unit tests | Tests for config, factories, chunking, freshness, scoring, health. | P0 | Not Started | Dev | 1 | Day 9 | PB-046
PB-059 | Phase 13 Testing | Testing | Frontend basic tests | App, theme switcher, chat page, sources page render tests. | P1 | Not Started | Dev | 0.8 | Day 9 | PB-052
PB-060 | Phase 13 Testing | Testing | End-to-end smoke test | Local ingest -> query -> answer -> trace works with demo data. | P0 | Not Started | Dev | 1 | Day 10 | PB-041, PB-044
PB-061 | Phase 14 Deployment | Infra | Finalize Docker production build | Frontend nginx build and backend Dockerfile work cleanly. | P0 | Not Started | Dev | 0.8 | Day 10 | PB-004, PB-051
PB-062 | Phase 14 Deployment | Docs | Create deployment guide | Render/Railway/Fly/VPS style deployment guide with env notes. | P1 | Not Started | Dev | 0.6 | Day 10 | PB-061
PB-063 | Phase 14 Deployment | Security | Add secrets and token handling notes | Docs explain OAuth tokens, env files, and what not to commit. | P0 | Not Started | Dev | 0.5 | Day 10 | PB-029, PB-054
PB-064 | Phase 14 Final QA | Testing | Run full command checklist | make setup/docker-up/test/ingest-demo documented with actual result. | P0 | Not Started | Dev | 0.5 | Day 10 | PB-060, PB-061
PB-065 | Phase 14 Final QA | Docs | Final README update | README has commands, architecture summary, known limitations, next steps. | P0 | Not Started | Dev | 0.5 | Day 10 | PB-064

## 10-Day Plan
Day | Theme | Main Outcomes | Exit Criteria | Related Task IDs
Day 1 | Foundation | Repo, FastAPI, React, Docker, config, tracker | Health endpoint and frontend boot | PB-001 to PB-009
Day 2 | MongoDB | Async Mongo layer, repos, indexes | Mongo health and CRUD repositories | PB-010 to PB-013
Day 3 | Vector + LLM | Qdrant and Gemini abstractions | Embed/search/generate path works | PB-014 to PB-021
Day 4 | Ingestion Core | Local connector, loaders, chunking, hashing | Sample files indexed | PB-022 to PB-027
Day 5 | Ingestion UI + Drive Docs | Sources UI and Drive setup docs | Local ingestion visible in UI | PB-028 to PB-030
Day 6 | Google Drive + Retrieval | Picker component, Drive connector, retrieval service | Drive source creates ingestion job | PB-031 to PB-036
Day 7 | LangGraph RAG | RAG graph, citations, query endpoint, chat UI | Ask question and get cited answer | PB-037 to PB-041
Day 8 | Trace + Scoring + UI | Trace timeline, scoring, dashboard, themes | Trace UI shows operational path | PB-042 to PB-052
Day 9 | Evaluation + Docs + Tests | Eval dashboard, docs, backend/frontend tests | Docs and tests present | PB-053 to PB-059
Day 10 | Deployment + QA | Prod Docker, deployment guide, smoke test | Full demo path works | PB-060 to PB-065

## Config Matrix
Variable | Required | Default/Example | Used By | Purpose | Notes
APP_NAME | Yes | PolicyBot Intelligence | Backend/Frontend | Application display name
APP_ENV | Yes | local | Backend | Environment mode | local/dev/prod
API_PREFIX | Yes | /api/v1 | Backend | API base prefix
BACKEND_CORS_ORIGINS | Yes | http://localhost:5173 | Backend | Allowed frontend origins | Comma-separated
MONGODB_URI | Yes | mongodb://mongodb:27017 | Backend | MongoDB connection string
MONGODB_DB | Yes | policybot | Backend | MongoDB database name
VECTOR_DB_PROVIDER | Yes | qdrant | Backend | Select vector DB provider | qdrant/pinecone/chroma/mongo
QDRANT_URL | Yes | http://qdrant:6333 | Backend | Qdrant service URL | Default local Docker
QDRANT_COLLECTION | Yes | policybot_chunks | Backend | Vector collection name
QDRANT_VECTOR_SIZE | Yes | 768 | Backend | Embedding vector dimension | Must match embedding model
LLM_PROVIDER | Yes | gemini | Backend | Select LLM provider | gemini/openai/anthropic/local
GEMINI_API_KEY | Yes for Gemini |  | Backend | Gemini API key | Secret; never commit
GEMINI_CHAT_MODEL | Yes | gemini-1.5-flash | Backend | Gemini chat model | Configurable
GEMINI_EMBEDDING_MODEL | Yes | text-embedding-004 | Backend | Gemini embedding model | Configurable
GOOGLE_CLIENT_ID | For Drive |  | Frontend/Backend | Google OAuth web client ID | Needed for Picker
GOOGLE_CLIENT_SECRET | For Drive |  | Backend | Google OAuth client secret | Secret; never commit
GOOGLE_API_KEY | For Picker |  | Frontend | Google Picker API key | Restrict in Google Cloud
GOOGLE_REDIRECT_URI | For Drive | http://localhost:8000/api/v1/google-drive/oauth/callback | Backend | OAuth callback | Must match Cloud Console
TRACE_ENABLED | Yes | true | Backend | Enable trace persistence
EVAL_ENABLED | Yes | true | Backend | Enable evaluation endpoints
LOG_LEVEL | Yes | INFO | Backend | Logging level

## API Checklist
Method | Endpoint | Purpose | Backend Status | Frontend Connected | Notes
GET | /api/v1/health | Health check | Not Started | Not Started | Mongo + Qdrant status
GET | /api/v1/config | Fetch runtime config | Not Started | Not Started | No secrets
PATCH | /api/v1/config | Update runtime config | Not Started | Not Started | Validate values
GET | /api/v1/sources | List sources | Not Started | Not Started | Local + Drive
POST | /api/v1/sources/local-folder | Create local source | Not Started | Not Started | Server path mode
POST | /api/v1/sources/google-drive | Create Drive source | Not Started | Not Started | From picker/folder sync
DELETE | /api/v1/sources/{source_id} | Delete source | Not Started | Not Started | Also delete vectors? configurable
POST | /api/v1/ingestion/jobs | Start ingestion job | Not Started | Not Started | Async job
GET | /api/v1/ingestion/jobs | List jobs | Not Started | Not Started | Progress table
GET | /api/v1/ingestion/jobs/{job_id} | Job details | Not Started | Not Started | Counts/logs
POST | /api/v1/query | Ask question | Not Started | Not Started | Returns answer/citations/scores/trace_id
GET | /api/v1/traces/{trace_id} | Trace details | Not Started | Not Started | Timeline payload
POST | /api/v1/evaluation/datasets | Create eval dataset | Not Started | Not Started | Golden Q&A
GET | /api/v1/evaluation/datasets | List eval datasets | Not Started | Not Started
POST | /api/v1/evaluation/run | Run evaluation | Not Started | Not Started
GET | /api/v1/evaluation/runs/{run_id} | Eval results | Not Started | Not Started
GET | /api/v1/google-drive/config | Drive client config | Not Started | Not Started | No secret
GET | /api/v1/google-drive/oauth/start | Start OAuth | Not Started | Not Started
GET | /api/v1/google-drive/oauth/callback | OAuth callback | Not Started | Not Started
POST | /api/v1/google-drive/picker-selection | Handle selected files | Not Started | Not Started
POST | /api/v1/google-drive/folder-sync | Start folder sync | Not Started | Not Started | May need broader scope

## Google Drive Flow
Step | Frontend Action | Backend Action | Data Stored | Security Note | Status
1 | User clicks Connect Google Drive | Return public Google config | No secrets | Only client ID/API key exposed | Not Started
2 | Frontend requests OAuth token | OAuth callback/token handling if backend mode used | Token reference/session | Use least-privilege scopes | Not Started
3 | Open Google Picker | N/A | Selected file/folder ids in UI state | Picker lets user choose explicit files/folders | Not Started
4 | User confirms Start Indexing | Create source + ingestion job | source record, job record | Do not store raw token unless encrypted | Not Started
5 | Show progress | List/download/export selected files | documents, versions, job logs | Respect file permissions | Not Started
6 | Display indexed files | Extract metadata, chunk, embed, upsert | chunks metadata + vectors | Never expose private Drive content in logs | Not Started
7 | Ask question | RAG searches selected Drive source | query session + trace | Citations must point to allowed source metadata | Not Started

## Testing Matrix
Test ID | Layer | Test Case | Expected Result | Priority | Status | Notes
T-001 | Backend | Health endpoint | Returns app, MongoDB, Qdrant health | P0 | Not Started
T-002 | Backend | Config loading | Valid env loads and invalid env fails clearly | P0 | Not Started
T-003 | Backend | Provider factory | Gemini provider returned for LLM_PROVIDER=gemini | P0 | Not Started
T-004 | Backend | Vector store factory | Qdrant returned for VECTOR_DB_PROVIDER=qdrant | P0 | Not Started
T-005 | Backend | Chunking | Chunks preserve source metadata and overlap config | P0 | Not Started
T-006 | Backend | Freshness resolver | Latest valid source selected when conflicts exist | P0 | Not Started
T-007 | Backend | Scoring | Scores are bounded 0-1 and explainable | P1 | Not Started
T-008 | Backend | Trace persistence | Every graph node writes trace event | P0 | Not Started
T-009 | Integration | Local ingest E2E | Sample folder indexed into MongoDB + Qdrant | P0 | Not Started
T-010 | Integration | Ask question E2E | Answer includes citations and trace id | P0 | Not Started
T-011 | Frontend | App renders | Routes render without crash | P0 | Not Started
T-012 | Frontend | Theme switcher | Theme changes and persists | P1 | Not Started
T-013 | Frontend | Chat page | Question input, answer card, citations visible | P0 | Not Started
T-014 | Frontend | Sources page | Local and Google Drive source cards visible | P0 | Not Started

## Risk Register
Risk ID | Risk | Impact | Probability | Mitigation | Owner | Status
R-001 | Google Drive folder sync may need broader OAuth scope | High | Medium | Implement file picker mode first; document folder sync scope difference. | Dev | Open
R-002 | Gemini embedding dimension mismatch with Qdrant config | High | Medium | Keep vector size configurable; validate on startup before upsert. | Dev | Open
R-003 | 10-day timeline too tight for full production polish | Medium | High | Build MVP path first, then Drive/eval/polish. | Dev | Open
R-004 | Large PDFs cause slow ingestion | Medium | Medium | Async jobs, chunk batching, progress logging, file size limits. | Dev | Open
R-005 | Trace UI may expose sensitive document content | High | Medium | Show snippets/citations carefully; do not log secrets or tokens. | Dev | Open
R-006 | Vector DB provider abstraction becomes leaky | Medium | Medium | Keep common search/upsert contract and provider-specific config isolated. | Dev | Open

## Lists
Status | Priority | Area | Target Day
Not Started | P0 | Backend | Day 1
In Progress | P1 | Frontend | Day 2
Blocked | P2 | Infra | Day 3
In Review | P3 | RAG | Day 4
Done |  | Vector DB | Day 5
|  | MongoDB | Day 6
|  | Google Drive | Day 7
|  | Docs | Day 8
|  | Testing | Day 9
|  | Evaluation | Day 10
Security
Observability